## RODC PLAN Original
Sl.no | Machine | Department | Source | Description | Task | Days Given | Start date | End date | Days taken
1 | RTS | Fabrication | In-house | LC welding | 1 | 3 | 2024-08-29 | 2024-08-31 | 3
2 | RTS | Fabrication | Out-Source | Drum rolling | 1 | 3 | 2024-08-26 | 2024-08-28 | 3
3 | RTS | Fabrication | Out-Source | L angle rolling | 1 | 1 | 2024-08-26 | 2024-08-26 | 1
4 | RTS | Fabrication | In-house | Flute welding | 1 | 4 | 2024-09-11 | 2024-09-14 | 4
5 | RTS | Fabrication | In-house | LC to drum | 1 | 6 | 2024-08-29 | 2024-09-04 | 6
6 | RTS | Fabrication | In-house | L angle to drum | 1 | 4 | 2024-09-05 | 2024-09-10 | 5
7 | RTS | Fabrication | In-house | RTS sand mesh | 1 | 2 | 2024-08-29 | 2024-08-30 | 2
8 | RTS | Assembly | In-house | Drum on frame | 1 | 2 | 2024-09-23 | 2024-09-24 | 2
9 | RTS | Assembly | In-house | Wheel and rod bearing | 1 | 1 | 2024-09-23 | 2024-09-23 | 1
10 | RTS | Assembly | In-house | Side frame | 1 | 1 | 2024-09-23 | 2024-09-23 | 1
11 | RTS | Assembly | In-house | Sand mesh | 1 | 1 | 2024-09-23 | 2024-09-23 | 1
12 | RTS | Paint | In-house | Frame | 1 | 9 | 2024-08-22 | 2024-09-01 | 9
13 | RTS | Paint | In-house | Drum | 1 | 10 | 2024-09-11 | 2024-09-21 | 10
14 | RTS | Paint | In-house | Basket | 1 | 3 | 2024-09-02 | 2024-09-04 | 3
15 | RTS | Paint | In-house | Side frame - paint | 1 | 3 | 2024-08-21 | 2024-08-22 | 2
16 | RTS | Paint | In-house | Mesh | 1 | 2 | 2024-09-05 | 2024-09-06 | 2
17 | RTS | Fabrication | Out-Source | RTS bracket | 1 | 7 | 2024-08-10 | 2024-08-17 | 7
18 | RTS | Fabrication | Out-Source | RTS frame | 1 | 7 | 2024-08-10 | 2024-08-17 | 7
19 | RTS | Fabrication | Out-Source | Wheel guard | 1 | 7 | 2024-08-10 | 2024-08-17 | 7
20 | RTS | Machining | Vendor | Moving Shaft | 1 | 4 | 2024-08-18 | 2024-08-22 | 4
21 | RTS | Machining | Vendor | Stationary shaft | 1 | 6 | 2024-08-18 | 2024-08-24 | 6
22 | RTS | Machining | Vendor | Sprocket | 1 | 2 | 2024-08-18 | 2024-08-20 | 2
23 | RTS | Machining | Vendor | Idler Shaft | 1 | 3 | 2024-08-18 | 2024-08-21 | 3
24 | RTS | Machining | Vendor | Flute machining | 1 | 6 | 2024-08-21 | 2024-08-27 | 6
25 | Slurry pot | Fabrication | In-house | Frame | 1 | 8 | 2024-08-26 | 2024-09-03 | 8
26 | Slurry pot | Fabrication | Out-Source | Drum | 1 | 11 | 2024-08-08 | 2024-08-20 | 11
27 | Slurry pot | Fabrication | In-house | Stirrer | 1 | 3 | 2024-08-21 | 2024-08-23 | 3
28 | Slurry pot | Fabrication | In-house | Cladding | 1 | 4 | 2024-09-04 | 2024-09-09 | 5
29 | Slurry pot | Assembly | In-house | Bearing box and base plate | 1 | 1 | 2024-09-10 | 2024-09-10 | 1
30 | Slurry pot | Assembly | In-house | Drum and base plate | 1 | 1 | 2024-09-10 | 2024-09-10 | 1
31 | Slurry pot | Assembly | In-house | Base plate on frame | 1 | 1 | 2024-09-10 | 2024-09-10 | 1
32 | Slurry pot | Assembly | In-house | Stirrer cladding | 1 | 1 | 2024-09-11 | 2024-09-11 | 1
33 | Slurry pot | Paint | In-house | Paint for drum | 1 | 10 | 2024-09-12 | 2024-09-23 | 10
34 | Slurry pot | Machining | Vendor | Bearing holder top | 1 | 10 | 2024-09-10 | 2024-09-20 | 10
35 | Slurry pot | Machining | Vendor | Bearing holder bottom | 1 | 8 | 2024-09-10 | 2024-09-17 | 7
36 | Slurry pot | Machining | Vendor | Base plate | 1 | 8 | 2024-09-10 | 2024-09-18 | 8
37 | Slurry pot | Machining | Vendor | Pulley | 1 | 2 | 2024-09-10 | 2024-09-11 | 2
38 | Conveyor | Fabrication | In-house | Frame | 1 | 18 | 2024-09-02 | 2024-09-23 | 19
39 | Conveyor | Fabrication | In-house | Guide LC Welding | 1 | 6 | 2024-09-24 | 2024-09-30 | 6
40 | Conveyor | Fabrication | In-house | Guide Welding | 1 | 6 | 2024-10-01 | 2024-10-08 | 7
41 | Conveyor | Fabrication | In-house | LC Chamfer | 1 | 3 | 2024-10-07 | 2024-10-09 | 3
42 | Conveyor | Fabrication | In-house | Chain link welding | 1 | 18 | 2024-09-02 | 2024-09-22 | 18
43 | Conveyor | Fabrication | In-house | Hanger link welding | 1 | 5 | 2024-09-24 | 2024-09-28 | 5
44 | Conveyor | Fabrication | In-house | Power pack tank | 1 | 4 | 2024-09-11 | 2024-09-14 | 4
45 | Conveyor | Fabrication | In-house | Push button station frame | 1 | 2 | 2024-09-20 | 2024-09-21 | 2
46 | Conveyor | Assembly | In-house | Chain assembly | 1 | 3 | 2024-09-30 | 2024-10-03 | 4
47 | Conveyor | Assembly | In-house | Hydraulic system assembly | 1 | 1 | 2024-09-25 | 2024-09-25 | 1
48 | Conveyor | Assembly | In-house | General assembly | 1 | 3 | 2024-10-29 | 2024-10-31 | 3
49 | Conveyor | Paint | In-house | Conveyor | 1 | 9 | 2024-10-09 | 2024-09-29 | 9
50 | Conveyor | Paint | In-house | Chain | 1 | 9 | 2024-10-09 | 2024-09-29 | 9
51 | Conveyor | Machining | In-house | Hub machining | 1 | 1 | 2024-09-10 | 2024-09-11 | 2
52 | Conveyor | Machining | In-house | Working end shaft | 1 | 3 | 2024-08-18 | 2024-08-21 | 3
53 | Conveyor | Machining | In-house | Moving end shaft | 1 | 3 | 2024-08-18 | 2024-08-21 | 3
54 | Conveyor | Machining | In-house | Top sprocket spacer | 1 | 3 | 2024-08-30 | 2024-09-03 | 4
55 | Conveyor | Machining | Out-Source | Outer link pin | 1 | 12 | 2024-08-11 | 2024-08-26 | 13
56 | Conveyor | Machining | Vendor | Chain end pin | 1 | 2 | 2024-08-30 | 2024-08-31 | 2
57 | Conveyor | Machining | Vendor | Inner tube | 1 | 12 | 2024-08-07 | 2024-08-21 | 13
58 | Conveyor | Machining | Vendor | Top bearing spacer | 1 | 5 | 2024-09-02 | 2024-09-07 | 6
59 | Conveyor | Machining | Vendor | Top bearing mounting shaft | 1 | 5 | 2024-09-02 | 2024-09-07 | 6
60 | Conveyor | Machining | Vendor | Ball transfer unit side spacer | 1 | 6 | 2024-08-30 | 2024-09-05 | 6
61 | Conveyor | Machining | Vendor | Trunnion ball mtg cage 1 | 1 | 10 | 2024-08-30 | 2024-09-11 | 11
62 | Conveyor | Machining | Vendor | Trunnion ball mtg cage 2 | 1 | 10 | 2024-08-30 | 2024-09-11 | 11
63 | Conveyor | Machining | Vendor | Trunnion ball | 1 | 10 | 2024-08-30 | 2024-09-11 | 11
64 | Conveyor | Machining | Vendor | Cylinder spacer | 1 | 10 | 2024-08-30 | 2024-09-11 | 11
65 | Conveyor | Machining | Vendor | Eye rod locking pin | 1 | 10 | 2024-08-30 | 2024-09-11 | 11
66 | Conveyor | Machining | Vendor | Ratchet guide bar | 1 | 10 | 2024-08-30 | 2024-09-11 | 11
67 | Conveyor | Machining | Vendor | Ratchet guide bush | 1 | 10 | 2024-08-30 | 2024-09-11 | 11
68 | Conveyor | Machining | Vendor | Ratchet pin | 1 | 10 | 2024-08-30 | 2024-09-11 | 11
69 | Conveyor | Machining | Vendor | Stopper pin | 1 | 10 | 2024-08-30 | 2024-09-11 | 11
70 | Gripper | Fabrication | In-house | Jaw welding | 1 | 1 | 2024-08-08 | 2024-08-08 | 1
71 | Gripper | Machining | Vendor | Top flange | 1 | 4 | 2024-08-08 | 2024-08-08 | 1
72 | Gripper | Machining | Vendor | Top spacer | 1 | 6 | 2024-08-08 | 2024-08-08 | 1
73 | Gripper | Machining | Vendor | Cylinder bottom flange | 1 | 4 | 2024-08-08 | 2024-08-08 | 1
74 | Gripper | Machining | Vendor | Piston | 1 | 1 | 2024-08-08 | 2024-08-08 | 1
75 | Gripper | Machining | Vendor | Piston rod | 1 | 1 | 2024-08-08 | 2024-08-08 | 1
76 | Gripper | Machining | Vendor | Gripper tip | 1 | 1 | 2024-08-08 | 2024-08-08 | 1
77 | Gripper | Machining | Vendor | Neckband | 1 | 2 | 2024-08-08 | 2024-08-08 | 1
78 | Gripper | Paint | In-house | Blackening | 1 | 1 | 2024-08-08 | 2024-08-08 | 1
79 | Control panel | Fabrication | In-House | Control panel frame | 1 | 2 | 2024-09-16 | 2024-09-17 | 2
80 | Control panel | Fabrication | Out-Source | Control panel fabrication | 1 | 10 | 2024-08-26 | 2024-09-05 | 10
81 | Control panel | Electrical | In-House | Robot and master control panel mounting | 1 | 1 | 2024-09-18 | 2024-09-18 | 1
82 | Control panel | Electrical | In-House | Components purchase | 1 | 10 | 2024-09-02 | 2024-09-13 | 11
83 | Control panel | Electrical | In-House | Control panel GA | 1 | 4 | 2024-09-19 | 2024-09-23 | 4
84 | Control panel | Electrical | In-House | Power wiring | 1 | 4 | 2024-09-24 | 2024-09-27 | 4
85 | Control panel | Electrical | In-House | Control wiring | 1 | 12 | 2024-09-28 | 2024-10-15 | 15
86 | Control panel | Electrical | In-House | Integration of control panel wiring | 1 | 2 | 2024-10-16 | 2024-10-17 | 2
87 | Control panel | Electrical | In-House | Stickering and legends | 1 | 1 | 2024-10-18 | 2024-10-18 | 1
88 | Control panel | Electrical | In-House | Outer wiring and sensor components mounting | 1 | 10 | 2024-10-19 | 2024-10-30 | 10
89 | Control panel | Electrical | In-House | Gripper pneumatic plates | 1 | 2 | 2024-10-22 | 2024-10-23 | 2
90 | Control panel | Electrical | In-House | Robot sensor and pneumatic lining | 1 | 1 | 2024-10-23 | 2024-10-23 | 1
91 | Dust collector | Fabrication | Out-Source | Frame | 1 | 14 | 2024-10-01 | 2024-10-20 | 17
92 | Dust collector | Fabrication | Out-Source | Air Encloser | 1 | 14 | 2024-10-01 | 2024-10-20 | 17
93 | Dust collector | Fabrication | In-House | Acutuator valve pipe line | 1 | 4 | 2024-10-21 | 2024-10-24 | 4
94 | Dust collector | Fabrication | In-House | Reverse pluse cylinder | 1 | 4 | 2024-10-25 | 2024-10-29 | 4
95 | Dust collector | Assembly | In-House | Door assembly | 1 | 1 | 2024-10-29 | 2024-10-29 | 1
96 | Dust collector | Assembly | In-House | Filter assembly | 1 | 1 | 2024-10-29 | 2024-10-29 | 1
97 | Dust collector | Paint | In-House | Primer & Paint | 1 | 3 | 2024-10-04 | 2024-10-07 | 3
98 | Robot Hanger Disc | Fabrication | In-House | Cluster hanger welding | 1 | 18 | 2024-09-01 | 2024-09-23 | 19
99 | Robot Hanger Disc | Fabrication | In-House | Pipe oil cleaning | 1 | 2 | 2024-09-26 | 2024-09-27 | 2
100 | Robot Hanger Disc | Machining | Vendor | Cutting of side pipe | 1 | 5 | 2024-08-08 | 2024-08-13 | 5
101 | Robot Hanger Disc | Machining | Vendor | Machining of center pipe | 1 | 5 | 2024-08-08 | 2024-08-13 | 5
102 | Robot Hanger Disc | Machining | Out-Source | Phosphating | 1 | 2 | 2024-09-24 | 2024-09-25 | 2
103 | Robot Hanger Disc | Fabrication | In-House | LC disc | 1 | 11 | 2024-08-12 | 2024-08-25 | 12
104 | Ready Hanger trolley | Fabrication | Out-Source | Frame | 1 | 14 | 2024-10-01 | 2024-10-20 | 17
105 | Ready Hanger trolley | Paint | In-House | Painting | 1 | 1 | 2024-10-29 | 2024-10-29 | 1
106 | Hanger Assembly Stand | Fabrication | Out-Source | Frame | 1 | 14 | 2024-10-01 | 2024-10-20 | 17
107 | Hanger Assembly Stand | Machining | Vendor | Shaft machining | 1 | 2 | 2024-10-23 | 2024-10-24 | 2
108 | Hanger Assembly Stand | Machining | Vendor | Bearing retainer machining | 1 | 2 | 2024-10-23 | 2024-10-24 | 2
109 | Hanger Assembly Stand | Paint | In-House | Painting | 1 | 1 | 2024-10-28 | 2024-10-28 | 1
110 | Conveyor enclosure | Fabrication | In-House | Frame 1 & Frame 2 LC RIB welding | 1 | 3 | 2024-10-23 | 2024-10-25 | 3
111 | Conveyor enclosure | Assembly | In-House | Polycarbonate sheet mounting | 1 | 3 | 2024-10-06 | 2024-10-09 | 3
112 | Conveyor enclosure | Paint | In-House | Painting & redoxide | 1 | 7 | 2024-10-26 | 2024-11-05 | 9
113 | Conveyor enclosure | Fabrication | Out-Source | 750 Conveyor encluser frame 1 | 1 | 14 | 2024-10-01 | 2024-10-20 | 17
114 | Conveyor enclosure | Fabrication | Out-Source | 750 Conveyor encluser frame 2 | 1 | 14 | 2024-10-01 | 2024-10-20 | 17
115 | Conveyor enclosure | Machining | Out-Source | 750 Conveyor fan frame | 1 | 14 | 2024-10-01 | 2024-10-20 | 17
116 | Conveyor enclosure | Machining | Out-Source | 750 Conveyor fan frame drum | 1 | 14 | 2024-10-01 | 2024-10-20 | 17
117 | Conveyor enclosure | Machining | Vendor | Conveyor fan blade | 1 | 6 | 2024-10-01 | 2024-10-08 | 7
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Holidays in a year
Holidays in a year
2024-08-15
2024-09-07
2024-10-02
2024-10-11
2024-10-12
2024-11-01
2024-11-02
2025-01-15
2025-01-26