## RODC STATUS Original
Sl.no | Machine | Department | Source | Description | Task | Days Given | Start date | End date | Days taken | Status 1 | Status 2 | Team
1 | RTS | Fabrication | In-house | LC welding |  | 3
2 | RTS | Fabrication | Out-Source | Drum rolling | 1 | 3 | 2024-08-28 | 2024-08-30 | 3 | On-time | Completed
3 | RTS | Fabrication | Out-Source | L angle rolling | 1 | 3 | 2024-08-28 | 2024-08-30 | 3 | On-time | Completed
4 | RTS | Fabrication | In-house | Flute welding |  | 4
5 | RTS | Fabrication | In-house | LC to drum |  | 6
6 | RTS | Fabrication | In-house | L angle to drum |  | 4
7 | RTS | Fabrication | In-house | RTS sand mesh |  | 2
8 | RTS | Assembly | In-house | Drum on frame |  | 2
9 | RTS | Assembly | In-house | Wheel and rod bearing |  | 1
10 | RTS | Assembly | In-house | Side frame |  | 1
11 | RTS | Assembly | In-house | Sand mesh |  | 1
12 | RTS | Paint | In-house | Frame |  | 10
13 | RTS | Paint | In-house | Drum | 1 | 10 | 2024-09-02 |  | In-Process | In-Process | In-Process
14 | RTS | Paint | In-house | Basket |  | 3
15 | RTS | Paint | In-house | Side frame - paint |  | 3
16 | RTS | Paint | In-house | Mesh |  | 2
17 | RTS | Fabrication | Out-Source | RTS bracket | 1 | 6 | 2024-08-11 | 2024-08-17 | 6 | On-time | Completed
18 | RTS | Fabrication | Out-Source | RTS frame | 1 | 6 | 2024-08-11 | 2024-08-17 | 6 | On-time | Completed
19 | RTS | Fabrication | Out-Source | Wheel guard | 1 | 6 | 2024-08-11 | 2024-08-17 | 6 | On-time | Completed
20 | RTS | Machining | Vendor | Moving Shaft | 1 | 4 | 2024-08-05 |  | In-Process | In-Process | In-Process
21 | RTS | Machining | Vendor | Stationary shaft |  | 6
22 | RTS | Machining | Out-Source | Sprocket | 1 | 1 | 2024-09-02 | 2024-09-02 | 1 | On-time | Completed | Vasu enterprises
23 | RTS | Machining | Vendor | Idler Shaft |  | 3
24 | RTS | Machining | Vendor | Flute machining | 1 | 6 | 2024-08-23 |  | In-Process | In-Process | In-Process
25 | Slurry pot | Fabrication | In-house | Frame | 1 | 8 | 2024-08-28 | 2024-09-05 | 8 | On-time | Completed | Ganesh team
26 | Slurry pot | Fabrication | Out-Source | Drum | 1 | 10 | 2024-08-26 | 2024-08-30 | 5 | On-time | Completed | Out-source
27 | Slurry pot | Fabrication | In-house | Stirrer | 1 | 3 | 2024-09-01 | 2024-09-03 | 2 | On-time | Completed
28 | Slurry pot | Fabrication | Out-Source | Cladding | 1 | 4 | 2024-08-28 | 2024-08-31 | 4 | On-time | Completed
29 | Slurry pot | Assembly | In-house | Bearing box and base plate |  | 1
30 | Slurry pot | Assembly | In-house | Drum and base plate | 1 | 1 | 2024-09-02 |  | In-Process | In-Process | In-Process | Ganesh team
31 | Slurry pot | Assembly | In-house | Base plate on frame |  | 1
32 | Slurry pot | Assembly | In-house | Stirrer cladding |  | 1
33 | Slurry pot | Paint | In-house | Paint for drum | 1 | 10 | 2024-09-10 | 2024-09-19 | 9 | On-time | Completed
34 | Slurry pot | Machining | Vendor | Bearing holder top |  | 10
35 | Slurry pot | Machining | Vendor | Bearing holder bottom |  | 8
36 | Slurry pot | Machining | Vendor | Base plate |  | 8
37 | Slurry pot | Machining | Vendor | Pulley |  | 2
38 | Conveyor | Fabrication | In-house | Frame |  | 18
39 | Conveyor | Fabrication | In-house | Guide LC Welding |  | 6
40 | Conveyor | Fabrication | In-house | Guide Welding |  | 6
41 | Conveyor | Fabrication | In-house | LC Chamfer |  | 3
42 | Conveyor | Fabrication | In-house | Chain link welding |  | 18
43 | Conveyor | Fabrication | In-house | Hanger link welding |  | 5
44 | Conveyor | Fabrication | In-house | Power pack tank |  | 4
45 | Conveyor | Fabrication | In-house | Push button station frame |  | 2
46 | Conveyor | Assembly | In-house | Chain assembly |  | 3
47 | Conveyor | Assembly | In-house | Hydraulic system assembly |  | 1
48 | Conveyor | Assembly | In-house | General assembly |  | 3
49 | Conveyor | Paint | In-house | Conveyor |  | 9
50 | Conveyor | Paint | In-house | Chain |  | 9
51 | Conveyor | Machining | Vendor | Hub machining |  | 1
52 | Conveyor | Machining | Vendor | Working end shaft | 1 | 3 | 2024-08-16 |  | In-Process | In-Process | In-Process
53 | Conveyor | Machining | Vendor | Moving end shaft | 1 | 3 | 2024-08-16 |  | In-Process | In-Process | In-Process
54 | Conveyor | Machining | Vendor | Top sprocket spacer |  | 3
55 | Conveyor | Machining | Vendor | Outer link pin | 1 | 12 | 2024-08-12 | 2024-08-24 | 12 | On-time | Completed
56 | Conveyor | Machining | Vendor | Chain end pin |  | 2
57 | Conveyor | Machining | Vendor | Inner tube | 1 | 12 | 2024-08-07 |  | In-Process | In-Process | In-Process
58 | Conveyor | Machining | Vendor | Top bearing spacer |  | 5
59 | Conveyor | Machining | Vendor | Top bearing mounting shaft |  | 5
60 | Conveyor | Machining | Vendor | Ball transfer unit side spacer |  | 20
61 | Conveyor | Machining | Vendor | Trunnion ball mtg cage 1 |  | 6
62 | Conveyor | Machining | Vendor | Trunnion ball mtg cage 2 |  | 6
63 | Conveyor | Machining | Vendor | Trunnion ball |  | 8
64 | Conveyor | Machining | Vendor | Cylinder spacer |  | 2
65 | Conveyor | Machining | Vendor | Eye rod locking pin |  | 3
66 | Conveyor | Machining | Vendor | Ratchet guide bar |  | 6
67 | Conveyor | Machining | Vendor | Ratchet guide bush |  | 6
68 | Conveyor | Machining | Vendor | Ratchet pin |  | 1
69 | Conveyor | Machining | Vendor | Stopper pin |  | 1
70 | Gripper | Fabrication | In-house | Jaw welding |  | 1
71 | Gripper | Machining | Vendor | Top flange |  | 4
72 | Gripper | Machining | Vendor | Top spacer |  | 6
73 | Gripper | Machining | Vendor | Cylinder bottom flange |  | 4
74 | Gripper | Machining | Vendor | Piston |  | 1
75 | Gripper | Machining | Vendor | Piston rod |  | 1
76 | Gripper | Machining | Vendor | Gripper tip |  | 1
77 | Gripper | Machining | Vendor | Neckband |  | 2
78 | Gripper | Paint | In-house | Blackening |  | 1
79 | Control panel | Fabrication | In-House | Control panel frame |  | 2
80 | Control panel | Fabrication | Out-Source | Control panel fabrication |  | 10
81 | Control panel | Electrical | In-House | Robot and master control panel mounting |  | 1
82 | Control panel | Electrical | In-House | Components purchase |  | 10
83 | Control panel | Electrical | In-House | Control panel GA |  | 4
84 | Control panel | Electrical | In-House | Power wiring |  | 4
85 | Control panel | Electrical | In-House | Control wiring |  | 12
86 | Control panel | Electrical | In-House | Integration of control panel wiring |  | 2
87 | Control panel | Electrical | In-House | Stickering and legends |  | 1
88 | Control panel | Electrical | In-House | Outer wiring and sensor components mounting |  | 10
89 | Control panel | Electrical | In-House | Gripper pneumatic plates |  | 2
90 | Control panel | Electrical | In-House | Robot sensor and pneumatic lining |  | 1
91 | Dust collector | Fabrication | Out-Source | Frame | 1 | 14 | 2024-08-24 |  | In-Process | In-Process | In-Process
92 | Dust collector | Fabrication | Out-Source | Air Encloser | 1 | 14 | 2024-08-24 |  | In-Process | In-Process | In-Process
93 | Dust collector | Fabrication | In-House | Acutuator valve pipe line |  | 4
94 | Dust collector | Fabrication | In-House | Reverse pluse cylinder |  | 4
95 | Dust collector | Assembly | In-House | Door assembly |  | 1
96 | Dust collector | Assembly | In-House | Filter assembly |  | 1
97 | Dust collector | Paint | In-House | Primer & Paint |  | 3
98 | Robot Hanger Disc | Fabrication | In-House | Cluster hanger welding |  | 18
99 | Robot Hanger Disc | Fabrication | In-House | Pipe oil cleaning |  | 2
100 | Robot Hanger Disc | Machining | Vendor | Cutting of side pipe | 1 | 5 | 2024-08-08 | 2024-08-13 | 5 | On-time | Completed
101 | Robot Hanger Disc | Machining | Vendor | Machining of center pipe | 1 | 5 | 2024-08-08 | 2024-08-13 | 5 | On-time | Completed
102 | Robot Hanger Disc | Machining | Out-Source | Phosphating |  | 2
103 | Robot Hanger Disc | Fabrication | In-House | LC disc | 1 | 2 | 2024-08-12 |  | In-Process | In-Process | In-Process
104 | Ready Hanger trolley | Fabrication | Out-Source | Frame |  | 14
105 | Ready Hanger trolley | Paint | In-House | Painting |  | 1
106 | Hanger Assembly Stand | Fabrication | Out-Source | Frame |  | 14
107 | Hanger Assembly Stand | Machining | Vendor | Shaft machining |  | 2
108 | Hanger Assembly Stand | Machining | Vendor | Bearing retainer machining |  | 2
109 | Hanger Assembly Stand | Paint | In-House | Painting |  | 1
110 | Conveyor enclosure | Fabrication | In-House | Frame 1 & Frame 2 LC RIB welding |  | 3
111 | Conveyor enclosure | Assembly | In-House | Polycarbonate sheet mounting |  | 3
112 | Conveyor enclosure | Paint | In-House | Painting & redoxide |  | 7
113 | Conveyor enclosure | Fabrication | Out-Source | 750 Conveyor encluser frame 1 |  | 14
114 | Conveyor enclosure | Fabrication | Out-Source | 750 Conveyor encluser frame 2 |  | 14
115 | Conveyor enclosure | Machining | Out-Source | 750 Conveyor fan frame |  | 14
116 | Conveyor enclosure | Machining | Out-Source | 750 Conveyor fan frame drum |  | 14
117 | Conveyor enclosure | Machining | Vendor | Conveyor fan blade |  | 12
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Holidays in a year
Holidays in a year
2024-08-15
2024-09-07
2024-10-02
2024-10-11
2024-10-12
2024-11-01
2024-11-02
2025-01-15
2025-01-26